## Addis Tech Website Tracker
Priority Order | Section | Issue Type | Description | Recommended Fix | Priority Level | Owner | Status
1 | Navbar | Visibility | Menu items not visible until scroll (low contrast) | Make text white + add semi-transparent background | High | Amen/Yoseph | Open
2 | Navigation Link | Functionality | 'Our Impact' link not working | Link to section or create page /impact | High | Amen/Yoseph | Open
3 | Contact Info | Content | Incorrect email shown | Replace with customerservice@addispcb.com | High | Amen/Yoseph | Open
4 | Social Links | Content | Wrong icons (Twitter/GitHub present) | Replace with LinkedIn, Facebook, Instagram | High | Amen/Yoseph | Open
5 | Social Links | Functionality | Links not connected | Link to correct Addis Tech pages | High | Amen/Yoseph | Open
6 | Icons/Card | UI Bug | Hover overlay covering icon | Fix z-index (icon above overlay) | High | Amen/Yoseph | Open
7 | Branding (Header) | Typography | Italic text used | Remove italics | Medium | Amen/Yoseph | Open
8 | Branding (Header) | Design | Glow/outline effect | Remove for clean look | Medium | Amen/Yoseph | Open
9 | Images (Design/Fabrication/Assembly) | Branding | Using stock images | Replace with real Addis Tech photos | Medium | Amen/Gobena | Open
10 | Images (Products) | Branding | Generic IoT stock image | Use Addis Nano / real prototypes | Medium | Amen/Gobena | Open
11 | Navbar | UX | Weak hover interaction | Add hover effect (color change) | Medium | Amen/Yoseph | Open
12 | Footer | Typography | Text is bold and all caps | Change to normal weight and sentence case | Low | Amen/Yoseph | Open
13 | Footer | Design | Too visually strong | Use softer color and smaller size | Low | Amen/Yoseph | Open